## 内容日历
阶段 | 日期 | 平台 | 内容主题 | 内容详情（英文发布） | 内容类型 | 配合素材 | 目标媒体/KOL互动 | 负责人 | 状态
会前预热 | 4/14 Mon | X | 倒计时预告 - "See you at B26" | The countdown is ON. FinTax is heading to #Bitcoin2026 in Las Vegas! 🎰 Come find us and learn how 150+ crypto enterprises manage accounting, tax & CARF compliance. 📍 The Venetian, Apr 27-29 #B26 #CryptoTax #CARF | 图文 | B26品牌主视觉海报 | @ Bitcoin Conference 官方 | 运营
会前预热 | 4/14 Mon | LinkedIn | 行业洞察 - CARF合规倒计时 | With 48 jurisdictions committed to CARF implementation by 2027, the clock is ticking for crypto exchanges worldwide. At Bitcoin 2026, our team will be sharing insights on how enterprises can prepare — from gap assessment to automated multi-jurisdiction reporting. Looking forward to connecting with compliance leaders in Las Vegas. | 长文 | CARF全球地图信息图 | Tag: OSL, Bybit, KuCoin等客户 | CEO/BD
会前预热 | 4/16 Wed | X | 产品亮点 - FinTax Suite | Managing crypto accounting across 70+ blockchains and 40+ exchanges? FinTax Suite automates 90% of bookkeeping workflows. SOC 1 & SOC 2 certified. Trusted by BGIN, GDA, BitFuFu and more. See it live at #Bitcoin2026 👇 [产品截图/GIF] | 图文/视频 | Suite产品截图或15s演示GIF | @ 客户官方账号 | 运营
会前预热 | 4/18 Fri | X | 团队亮相 - Meet the Team | Our team is packing for Vegas! 🧳 With backgrounds spanning Big 4 accounting firms, NYSE-listed companies & 10+ years in crypto tax... We're ready to talk CARF, cross-border structuring & enterprise crypto accounting. DM us to book a meeting at #Bitcoin2026 | 图文 | 团队成员合照/拼图 |  | CEO
会前预热 | 4/18 Fri | LinkedIn | 思想领导力 - Crypto Accounting挑战 | The 3 biggest barriers in crypto accounting today: 1. On-chain data is raw & noisy — fragmented sources, inconsistent formats 2. Accounting frameworks can't keep up — IFRS/GAAP lag behind crypto business models 3. Dual ledgers don't talk to each other — ERPs weren't built for crypto This is exactly why we built FinTax Suite. Happy to discuss at Bitcoin 2026 next week. | 长文 | Suite架构图 | Tag行业KOL | CTO
会前预热 | 4/21 Mon | X | 客户背书 - Client Testimonials | "FinTax is becoming an indispensable layer of infrastructure for Web3 operations." — Lim Danny, Founder, Pundi AI Proud to serve 150+ leading crypto organizations. See what we can do for yours at #Bitcoin2026. #CryptoAccounting #TaxCompliance | 引用卡片 | 客户证言设计卡片 | @ Pundi AI, @ NGC Ventures | BD
会前预热 | 4/21 Mon | LinkedIn | 预约会议号召 | Heading to Bitcoin 2026 in Las Vegas? Whether you're an exchange navigating CARF deadlines, a fund needing audit-ready financials, or a project planning cross-border tax structure — our team would love to connect. 📩 Book a meeting: [link] #Bitcoin2026 #CryptoCompliance | 图文 | 会议预约链接+二维码 |  | BD
会前预热 | 4/23 Wed | X | 产品亮点 - FinTax Calculator | CARF deadline: 2027. Time to prepare: NOW. FinTax Calculator helps exchanges: ✅ Auto-adapt to multi-jurisdiction tax rules ✅ Transform raw data into compliant reports ✅ Expert guidance from day one Demo at #Bitcoin2026 → DM us #CARF #1099DA | 图文 | Calculator产品截图 | @ 交易所客户 | 运营
会前预热 | 4/25 Fri | X | 最终预热 - "48 hours to go" | 48 hours until #Bitcoin2026! 🔥 FinTax will be at The Venetian. Here's what we're bringing: 🔹 Live demos of FinTax Suite & Calculator 🔹 1-on-1 CARF compliance consultations 🔹 Insights on cross-border crypto tax planning See you there! 🤝 | 图文 | 活动日程一图流 |  | 运营
会前预热 | 4/25 Fri | LinkedIn | 活动预览长文 | Bitcoin 2026 starts Monday. Here's what our team is most excited about: The convergence of crypto and traditional finance is accelerating. With CARF going live across 48 jurisdictions in 2027, the compliance infrastructure gap is becoming the industry's most pressing challenge. We'll be sharing how FinTax helps enterprises bridge this gap — from standardized on-chain data to automated multi-jurisdiction reporting. Looking forward to seeing old friends and meeting new ones in Las Vegas. | 长文 | 公司介绍单页PDF |  | CEO
活动期间 | 4/27 Mon AM | X | Day 1 开场 - We're Live! | We're LIVE at #Bitcoin2026! 🎰 Day 1 at The Venetian. Come say hi and get a firsthand look at how 150+ crypto enterprises handle accounting & compliance. 📍 [展位号/位置] #B26 #LasVegas | 现场图 | 展位/签到现场照片 | @ Bitcoin Conference | 运营
活动期间 | 4/27 Mon PM | X | 现场互动 - 产品演示精彩瞬间 | Great conversations happening at our booth today! 🔥 Showing exchanges how FinTax Calculator can cut CARF preparation time by months. Still time to swing by! [展位位置] #Bitcoin2026 | 现场图/短视频 | 演示+观众互动照片 | Tag 到场嘉宾 | 运营
活动期间 | 4/27 Mon | LinkedIn | Day 1 回顾 + 行业观察 | Day 1 at Bitcoin 2026 — key takeaway: Compliance is no longer a back-office afterthought. Every conversation today — from exchanges to funds to L1 projects — circles back to one question: "How do we get ready for CARF?" Proud that FinTax is positioned to help. More tomorrow. | 长文 | 精选现场图2-3张 |  | CEO
活动期间 | 4/28 Tue AM | X | Day 2 - 客户合影/会面 | Day 2 highlight: connecting with our amazing clients and partners at #Bitcoin2026! From mining giants to top exchanges — building the compliance layer for crypto, together. 🤝 [合影] | 合影图 | 与客户合影 | @ 出现的客户/合作伙伴 | BD
活动期间 | 4/28 Tue PM | X | 行业话题互动 - CARF热度 | The most asked question at our booth today: "We know CARF is coming, but where do we even start?" Our answer: Start with a compliance gap assessment. FinTax has helped exchanges across HK, Singapore & EU get audit-ready. DM us — even after #Bitcoin2026 ends. #CARF #CryptoCompliance | 文字 | 无/可配CARF信息图 |  | BD
活动期间 | 4/28 Tue | LinkedIn | Day 2 深度洞察 | Day 2 at Bitcoin 2026 — a clear theme is emerging: The crypto industry is professionalizing fast. The enterprises winning today aren't just building great products — they're building compliant, auditable, institutionally-ready operations. This is the future FinTax has been building toward for 10 years. | 长文 | 精选现场图 | Tag 对话过的行业领袖 | CEO
活动期间 | 4/29 Wed AM | X | Day 3 最终日 - 最后机会 | Final day at #Bitcoin2026! ⏰ Last chance to: 🔹 See FinTax Suite & Calculator live 🔹 Get a free CARF readiness assessment 🔹 Meet our Big 4-experienced tax team Catch us before we fly out! ✈️ | 图文 | 团队现场图 |  | 运营
活动期间 | 4/29 Wed PM | X | 闭幕感谢 - That's a Wrap! | That's a wrap on #Bitcoin2026! 🙌 Incredible 3 days in Vegas: ✅ 100+ meaningful conversations ✅ Live demos to exchanges, funds & projects ✅ Deep dives on CARF, cross-border tax & crypto accounting Thank you to everyone who stopped by. This is just the beginning. 🚀 | 现场图合集 | 3天精选图拼图 | @ 合作伙伴 & 媒体 | CEO
活动期间 | 4/29 Wed | LinkedIn | 活动总结 + CEO感言 | Bitcoin 2026 — done. Three days, hundreds of conversations, one clear signal: the demand for professional crypto financial infrastructure has never been stronger. From mining operators to licensed exchanges to global funds — every organization we spoke with is preparing for a more regulated, more institutional future. At FinTax, we're proud to be the compliance and accounting backbone for 150+ of these organizations. Thank you to our clients, partners, and the Bitcoin community. See you at the next one. | 长文 | 活动精选图3-5张 | Tag 所有见过的重要人物 | CEO
会后跟进 | 4/30 Wed | X | 花絮回顾 - Best Moments | Our favorite moments from #Bitcoin2026 🧵👇 1/ Setting up the booth before the crowd arrived 2/ Live-demoing FinTax Suite to exchange compliance teams 3/ Meeting [客户名] face-to-face for the first time 4/ The energy when everyone realized CARF preparation can't wait Thank you Las Vegas! Until next time. | 图文Thread | 每条配一张图 | @ 出现的所有人 | 运营
会后跟进 | 4/30 Wed | LinkedIn | 会后深度文章 - Key Takeaways | My top 3 takeaways from Bitcoin 2026: 1. CARF is the new KYC — compliance isn't optional, and the preparation window is closing fast 2. Crypto accounting is becoming a board-level conversation — CFOs and auditors are driving the agenda 3. The winners will be enterprises that invest in infrastructure now, not when deadlines hit If any of this resonates, let's connect. Our team is ready to help you get audit-ready. | 长文 | 活动照片 |  | CEO
会后跟进 | 5/2 Fri | X | 产品更新/功能预告 | Inspired by conversations at #Bitcoin2026, we're accelerating our roadmap: 🔹 Enhanced multi-jurisdiction CARF reporting 🔹 Deeper ERP integrations 🔹 New audit trail features for institutional clients Stay tuned. Big things coming. 💪 #FinTax #CryptoAccounting | 图文 | 产品路线图信息图 |  | CTO
会后跟进 | 5/2 Fri | LinkedIn | 客户案例分享 | One conversation at Bitcoin 2026 perfectly captures the challenge: A major exchange told us they had 6 months to become CARF-compliant across 3 jurisdictions — and no internal system to handle transaction-level reporting. This is exactly the problem FinTax solves. Our CARF compliance solution covers end-to-end: gap assessment, data standardization, automated reporting, and multi-jurisdiction filing. If you're facing similar deadlines, reach out. | 长文 | CARF解决方案流程图 |  | BD
会后跟进 | 5/5 Mon | X | 合作伙伴感谢 | Shoutout to the amazing partners and clients we connected with at #Bitcoin2026! 🙏 Building the financial infrastructure layer for crypto isn't a solo mission — it takes an ecosystem. Proud to work alongside industry leaders pushing for transparency and compliance. | 图文 | 合作伙伴logo墙 | @ 所有合作伙伴 | BD
会后跟进 | 5/5 Mon | LinkedIn | 行业趋势深度分析 | Post-Bitcoin 2026 reflection: The crypto tax and compliance market is projected to grow 500% over the next 5 years. Here's why: • 70+ jurisdictions adopting CARF • Traditional finance entering crypto (RWA, stablecoins, tokenized securities) • Institutional investors demanding audit-ready operations At FinTax, we've been preparing for this moment for 10 years. Now serving 150 clients with $7.5M in revenue — and we're just getting started. | 长文 | 市场增长数据图 |  | CEO
会后跟进 | 5/7 Wed | X | 媒体报道转发/汇总 | Honored to be featured in [媒体名] coverage of #Bitcoin2026! 📰 "[简短引用]" Thank you for shining a light on crypto compliance infrastructure. Full article: [link] | 转发/引用 | 媒体报道截图 | @ 报道媒体 | 运营
会后跟进 | 5/9 Fri | X + LinkedIn | 总结收官 - "What's Next" | One week since Bitcoin 2026. Here's what happened next: 📊 [X] new partnership discussions initiated 🤝 [X] demo requests received 📈 [X] CARF assessment consultations booked The momentum is real. If you missed us in Vegas, we're always a DM away. www.fintax.tech ¦ contact@fintax.tech | 数据图 | 成果数据信息图 |  | CEO

## 媒体互动计划
阶段 | 时间 | 媒体/KOL | 媒体层级 | 互动方式 | 内容角度 | 目标产出 | 负责人 | 状态
会前 | 4/14-18 | CoinDesk | T2-行业头部 | 新闻稿投递 | FinTax参加B26 + CARF合规解决方案发布 | 新闻报道/采访 | BD
会前 | 4/14-18 | Cointelegraph | T2-行业头部 | 新闻稿投递 | CARF 2027 deadline对交易所的影响 + FinTax方案 | 专题文章/引用 | BD
会前 | 4/14-18 | Benzinga | T1-主流财经 | 新闻稿投递 | 加密行业合规基础设施的蓝海市场 | 新闻报道 | BD
会前 | 4/14-18 | Investopedia | T1-主流金融 | 专家采访申请 | CARF是什么？对普通加密投资者意味着什么 | 引用/专家观点 | CEO
会前 | 4/14-18 | Channel 4 News UK | T1-主流电视 | 采访邀约 | 全球加密税务监管趋势 + 英国CARF实施 | 电视采访/报道 | CEO
会前 | 4/21-25 | Bitpush News | T3-中英媒体 | 中英文新闻稿 | FinTax亮相B26 + 服务150+企业客户里程碑 | 中英文报道 | BD
会前 | 4/21-25 | CriptoTendencia | T3-西语媒体 | 英文新闻稿 | CARF合规方案面向拉美/西班牙市场 | 西语报道 | BD
会前 | 4/21-25 | The Cryptonomist | T3-意/英媒体 | 新闻稿投递 | 欧洲CARF合规 + FinTax解决方案 | 英文/意文报道 | BD
会前 | 4/21-25 | EFN Finansmagasinet | T3-瑞典财经 | 新闻稿投递 | 北欧加密税务合规趋势 | 瑞典语报道 | BD
会前 | 4/21-25 | Kleine Zeitung | T3-奥地利日报 | 新闻稿投递 | 欧盟CARF实施对加密行业的影响 | 德语报道 | BD
活动期间 | 4/27 | BlockHash Podcast | T4-加密播客 | 播客采访 | CEO谈加密税务合规的未来 + FinTax创业故事 | 播客节目 | CEO
活动期间 | 4/27-28 | 现场加密KOL | T4-KOL | 展位来访+社媒互动 | 产品现场演示 + 合影 | 社媒发帖/转发 | 运营
活动期间 | 4/28 | CoinDesk/Cointelegraph | T2-行业头部 | 现场采访 | 活动期间CEO/CTO深度采访 | 采访文章/视频 | CEO
活动期间 | 4/27-29 | AFP (法新社) | T1-国际通讯社 | 现场接触 | 加密行业合规基础设施发展（行业角度） | 新闻通稿引用 | CEO
活动期间 | 4/27-29 | Crypto India Magazine | T3-印度市场 | 采访/产品介绍 | FinTax在亚太市场的布局 | 印度市场报道 | BD
会后 | 4/30-5/2 | CoinDesk | T2-行业头部 | 跟进稿件 | B26 Recap: CARF成为最热议题 + FinTax视角 | 深度文章 | BD
会后 | 4/30-5/2 | CzechCrunch | T3-捷克科技 | 新闻稿投递 | 加密税务科技创业 + FinTax增长故事 | 捷克语报道 | BD
会后 | 5/2-9 | 所有互动过的媒体 | 全层级 | 感谢邮件+后续素材 | 提供补充数据、图片、引用 | 维护关系/后续报道 | BD
会后 | 5/5-9 | ALM ThinkAdvisor | T3-金融顾问 | 专家投稿 | 加密时代财务顾问的合规指南 | 专栏文章 | CEO

## 素材准备清单
素材名称 | 类型 | 用途 | 所需内容 | 完成截止 | 负责人 | 状态
B26品牌主视觉海报 | 设计 | X/LinkedIn倒计时帖 | FinTax Logo + B26 + Las Vegas元素 + 日期 | 4/11 | 设计
CARF全球地图信息图 | 设计 | LinkedIn行业洞察帖 | 48国CARF承诺地图 + 2027 deadline标注 | 4/11 | 设计
Suite产品截图/GIF | 截图/视频 | X产品亮点帖 | Dashboard + 关键功能截图或15s演示GIF | 4/13 | 产品
Calculator产品截图 | 截图 | X产品亮点帖 | CARF报告生成界面截图 | 4/13 | 产品
团队成员照片/拼图 | 照片 | X团队亮相帖 | CEO + CTO + BD团队正式照 | 4/13 | HR
客户证言设计卡片 | 设计 | X客户背书帖 | 4位客户证言 (BGIN, NGC, MicroBT, Pundi AI) | 4/15 | 设计
会议预约链接/二维码 | 链接 | LinkedIn预约帖 | Calendly或类似工具链接 | 4/15 | BD
公司介绍单页PDF | 文档 | LinkedIn附件 + 现场派发 | 英文一页纸 (产品、客户、数据) | 4/18 | BD
Suite架构图 | 设计 | LinkedIn技术帖 | 数据流+功能模块架构图 | 4/15 | 产品
活动日程一图流 | 设计 | X最终预热帖 | FinTax在B26的3天安排一览 | 4/22 | 设计
英文新闻稿 (通用版) | 文档 | 发送给T1-T3媒体 | 公司介绍+B26参展+CARF方案亮点+数据 | 4/11 | BD
英文新闻稿 (CARF专题) | 文档 | 发送给合规/金融类媒体 | CARF deadline + FinTax解决方案 + 案例 | 4/11 | BD
中英文新闻稿 (亚太版) | 文档 | 发送给Bitpush等亚太媒体 | 含中文版 + 亚太市场数据 | 4/18 | BD
媒体资料包 (Media Kit) | 压缩包 | 发送给所有媒体 | Logo + 产品截图 + 团队照 + 新闻稿 + 数据 | 4/18 | 运营
产品路线图信息图 | 设计 | 会后X产品更新帖 | 2026 H2产品路线图可视化 | 4/25 | 产品
合作伙伴Logo墙 | 设计 | 会后X感谢帖 | 所有客户logo (已获授权) | 4/25 | 设计
市场增长数据图 | 设计 | 会后LinkedIn趋势分析帖 | 500%增长 + 70+jurisdictions + 客户数据 | 4/28 | 设计
成果数据信息图 | 设计 | 收官帖 | B26成果数据 (会面数、demo数等) | 5/5 | 运营

## KPI追踪
指标 | 会前目标 (4/14-26) | 活动期间目标 (4/27-29) | 会后目标 (4/30-5/9) | 总目标 | 实际值 | 完成率
X 发帖数 | 10 | 8 | 5 | 23
LinkedIn 发帖数 | 5 | 3 | 4 | 12
X 总曝光量 (impressions) | 50K | 100K | 30K
LinkedIn 总曝光量 | 20K | 50K | 20K
新增 X 粉丝 | 200 | 500 | 100 | 800
新增 LinkedIn 粉丝 | 100 | 200 | 100 | 400
媒体新闻稿发送数 | 10 | 0 | 5 | 15
媒体报道/提及数 | 2 | 3 | 3 | 8
播客采访完成数 | 0 | 1 | 1 | 2
现场会面/Demo数 | 0 | 50 | 0 | 50
会议预约数 | 20 | 0 | 10 | 30
网站流量增长 (%) | 20% | 50% | 30%